## Sheet1
PROJECT PETHUB
| TASK (ACTIVITIES) | DURATION | START | FINISH | PREDECESSORS | RESOURCE(S) | BUDGET | ACTUAL START | ACTUAL FINISH | % COMPLETE | JANUARY 2026 | [19 empty] | 2026-02-01 | [19 empty] | 2026-03-01
[11 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10
[11 empty] | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F
INITIATE
1 | Receive project mandate | 1 day | 2026-01-05 | 2026-01-05 | 0 | PM | 24.6 | 2026-01-05 | 2026-01-05 | 100
2 | Define roles and responsibilities | 1 day | 2026-01-06 | 2026-01-06 | 1 | PM | 34.85 | 16/1/2026 | 16/1/2026 | 100
3 | Plan project approach | 1 day | 2026-01-07 | 2026-01-07 | 2 | PM, Project planner | 49.3 | 19/1/2026 | 19/1/2026 | 100
4 | Create PID | 2 days | 2026-01-08 | 2026-01-09 | 3 | PM | 91.75 | 19/1/2026 | 19/1/2026 | 100
5 | Commence raids | 1 day | 2026-01-12 | 2026-01-12 | 4 | PM, PMO, BA,Hybrid | 29.4 | 20/01/2026 | 23/1/2026 | Ongoing
6 | Collate all reports | 1 day | 13/1/2026 | 13/1/2026 | 5 | PMO, Hybrid | 31.1 | 21/01/2026 | 23/01/2026 | Ongoing
7 | Create preliminary project plan/ Allocate Budget and resources | 1 day | 14/1/2025 | 14/1/2026 | 6 | PM, Project planner | 61.25 | 21/01/2026 | 2026-01-24 | Ongoing
8 | Schedule Initial elicitation of requirements | 1 day | 15/1/2026 | 15/1/2026 | 7 | BA, Hybrid | 36.4 | 2026-01-19 | 2026-01-19 | Complete
9 | Create Highlevel requirement list | 1day | 16/1/2026 | 16/1/2026 | 8 | BA, Hybrid | 44.9 | on going | on going | 0
10 | Create Project charter | 1 day | 16/1/2026 | 16/1/2026 | 9 | PM, Project planner | 54.35 | on going | on going | 0
11 | Document existing process flow (If required) | 1 day | 16/1/2026 | 16/1/2026 | 10 | BA, Hybrid | 59.8 | on going | on going | 0
12 | Gap Analysis (If required) | 1 day | 16/1/2026 | 16/1/2026 | 11 | BA, Hybrid | 69.65 | on going | on going | 0
13 | Propose new processes | 1 day | 16/1/2026 | 16/1/2026 | 12 | BA, Hybrid | 75.2 | on going | on going | 0
14 | Baseline Definitive project plan | 1 day | 16/1/2026 | 16/1/2026 | 13 | PM, project planner | 65.45 | on going | on going | 0
15 | Create business case | 1 day | 16/1/2026 | 16/1/2026 | 14 | BA, Hybrid | 94.9 | on going | on going | 0
16 | End stage report/ sign off | 1 day | 16/1/2026 | 16/1/2026 | 15 | PM | 57.1 | on going | on going | 0
DEFINE
17 | Create Epic list/Feature mapping | 2 days | 19/1/2026 | 20/1/2026 | 16 | BA, Hybrid | 218.6 | on going | on going | 0
18 | Create Use Case Diagram | 2 days | 21/1/2026 | 22/1/2026 | 17 | BA, Hybrid | 262.4 | on going | on going | 0
19 | Document benefit review plan | 1 day | 23/1/2026 | 23/1/2026 | 18 | BA, Hybrid | 179.75 | on going | on going | 0
20 | Create business requirement document | 3 days | 26/1/2026 | 28/1/2026 | 19 | BA, Hybrid | 421.9 | on going | on going | 0
21 | Write User stories & acceptance criteria | 1 day | 29/1/2026 | 29/1/2026 | 20 | BA, Hybrid | 357.85 | on going | on going | 0
22 | End stage report/ sign off | 1 day | 30/1/2026 | 30/1/2026 | 21 | PM | 119.5 | on going | on going | 0
EXECUTE
23 | Create wireframes (UI/UX) | 3days | 2026-02-02 | 2026-04-02 | 22 | BA, Hybrid | 518.75 | on going | on going | 0
24 | Create test cases | 3days | 2026-05-02 | 2026-09-02 | 23 | BA, Hybrid | 563.4 | on going | on going | 0
25 | Product backlog refinement | 2 days | 2026-10-02 | 2026-11-02 | 24 | PO,BA, Hybrid | 417.6 | on going | on going | 0
26 | Create definition of ready checklist | 1 day | 2026-12-02 | 2026-12-02 | 25 | BA, Hybrid | 258.35 | on going | on going | 0
27 | Sprint planning/Estimate user stories with developer/WBS | 1 day | 13/2/2026 | 13/2/2026 | 26 | Scrum team | 381.9 | on going | on going | 0
28 | Sprints (Daily Scrum) | 8 days | 16/2/2026 | 25/2/2026 | 27 | Scrum team | 1547.8 | on going | on going | 0
29 | Scrum Event (Product Testing/sprint Review) optional | 0.5 day | 26/2/2026 | 26/2/2026 | 28 | Scrum team | 319.65 | on going | on going | 0
30 | Scrum Event (Sprint Retrospective) | 0.5 day | 26/2/2026 | 26/2/2026 | 29 | Scrum team | 318.9 | on going | on going | 0
31 | Go live | 1 day | 27/2/2026 | 27/2/2026 | 30 | Scrum team, sponsor | 353.65 | on going | on going | 0
CLOSE
32 | Update business case | 1 day | 2026-02-03 | 2026-02-03 | 31 | PO/BA, hybrid | 108.85 | on going | on going | 0
33 | Client acceptance form | 1 day | 2026-03-03 | 2026-03-03 | 32 | PM, BA lead | 94.4 | on going | on going | 0
34 | Close all RAIDS | 2 days | 2026-04-03 | 2026-05-03 | 33 | PM, PMO,BA, hybrid | 86.3 | on going | on going | 0
35 | Document Lessons learnt | 2 days | 2026-06-03 | 2026-09-03 | 34 | PM, PMO, Hybrid | 121.75 | on going | on going | 0
36 | Post implementation review | 2 days | 2026-10-03 | 2026-11-03 | 35 | PM, BA,PMO,Hybrid | 159.6 | on going | on going | 0
37 | Upload all reports and deliverables | 1 day | 2026-12-03 | 2026-12-03 | 36 | PMO, BA Lead | 69.35 | on going | on going | 0
38 | Closure report | 1 day | 13/3/2026 | 13/3/2026 | 37 | PM | 139.75 | on going | on going | 0
| ALLOCATED WORKING BUDGET | [5 empty] | 7800
PLEASE NOTE TEAM:
CLOSURE 10%- $780
CONTINGENCY BUDGET - $1000
DEFINE 20%- $1560
EXECUTE 60%- $4680
INITIATE 10%- $780
WORKING BUDGET - $7,800
PLEASE NOTE THAT THE WEEKENDS ARE EXCLUDED FROM PROJECT SCHEDULE