## Slide 1
Project Information |  | 
Report Date | Project Title | Project Lead (Project Manager)
30-01 – 2026 | Project PETHUB | Chinelo Nnachetam-Agbo
Project Timeline |  |  |  | Project Budget |  |  | 
Start date | 05-01-2026 |  |  | Budget | $8,800 | Revised Budget | N/A
End date | 13-03-2026 | Revised End date | N/A | Forecast | $7,800 |  | 
Tolerance | None |  |  | Expenditure to date | $508.87 |  | 
RAG STATUS
Project Stage
Initiate
Define
Execute
Closure
Deliverable/Milestone | Due Date | RAG | Summary | Next Steps/ Path to Green
D- High Level Requirements | 30-01-2026 |  | Work ongoing with BA Team | Complete quickly and pass to BSA for sign off
D- AS IS Process Flow Map | 30-01-2026 |  | Work ongoing with BA / HybridTeam | All hands on deck and pass to BSA for sign off
D – TO BE Process Flow Map | 30-01-2026 |  | Work ongoing with BA / Hybrid Team | All hands on deck and pass to BSA for sign off
High & Severe Risks and Issues Escalation | 
Risk (R) Issue (I) | Mitigation (M) Resolution (R)
R -Team Members unavailable thereby delaying execution of allocated tasks. | M -Maintain a resource backup plan and/or identify alternate team members for critical roles. PM engagement and follow up.
R-Time management may lead to missed deadlines and delayed deliverables. | M -Clarify priorities, assign clear ownership, and monitor progress weekly.
I-Inexperienced Team Members | R – PSA Dorcas provide training and feedback during meeting and signposted resources and Templates on TDL and BaseCamp to assist Project members.
1. Programme Office to assist the PetHub Team in chasing other Project members. 2. Support from the Programme Office is required to grant access to archived projects, enabling the team to reference previous work for ideas and best practice.

## Slide 2
RAG STATUS DEFINITIONS
GREEN
RED
AMBER
Product delivery complete, benefit realized, client acceptance received, project closure documentation completed.
Off track, I have identified issues which may impact the scope or delivery schedule but have identified actions to mitigate them and these are now in place
I am on track to meet my agreed scope or delivery schedule.
BLUE
Off track, I am not going to meet the scope, budget or delivery schedule and will be submitting A Change or Exception Request for Programme Office approval.

## Slide 3
STATUS REPORT GUIDANCE NOTES
Start/ End date | Start Date: Enter the official start date of your project. End Date: Enter the planned completion date. Revised End Date: complete only if a new date is approved due to an extension. (If there is no revised end date, write N/A)
Budget | Budget: Enter the budget approved at the initiation stage by the Programme Office. Revised Budget: complete only if additional funding is approved, add it to the initial budget and record the new total. (If there is no revised budget, write N/A) Example: If the initial budget is £2,000 and an additional £500 is approved, the revised budget will be £2,500.
Project stage | Use Tritek’s RAG status definitions to assign and colour code the status of the current stage of your project.
Deliverables / Milestone | Deliverables/ Milestones - add key deliverables/milestone due in the reporting week. Summary - Provide a summary of the progress achieved. Next Steps - indicate the next steps or path to green
Risks/Issues | Prefix each Risk with (R) and Mitigation with (M) Prefix each Issue with (I) and Resolution with (R) Mitigation is the specific action planned to respond to risk raised. Resolution is the action or decision taken to address an issue raised .

## Slide 4: PM Support Meeting Terms of Reference
Purpose: The primary purpose of the Programme status report meeting is to provide a concise, high-level update on designated projects’ progress, ensuring alignment among team members and stakeholders, facilitating early risk identification, promoting accountability, and serving as a forum to gather support or request decisions.
Scope
Conduct Project Stage Performance Review and Project Health against Project Timeline, Budget, Assignment Forecast and Expenditure to date.
Review Progress Report on Deliverables & Milestone in line with framework, Next steps & Path to green.
Monitor Team’s adherence to governance process and best practices
Review escalated Risk & Issues
Review other Escalations to Programme Office.
End of Project Final Report, & Lessons Learned
Review Project Quality Assurance for the past two weeks.
Input
Use of right template & formatting
Clear, concise presentation by Project Lead or Rep
Introduction to the Project Mandate
Project Status Update – Overall RAG at current stage, key deliverables & milestone RAG, blockers & next steps
Escalated risk and issues
New & Existing Escalations pending decisions
Questions
Frequency: Fortnightly
Time: 8.00pm
Location: Tritek’s Zoom Conference
Quorate
Programme Office Facilitators – Chair
Project Lead or Representative - Presenter
Project Support Analyst
Project Team Members
Programme Managers
Output
Specific Project Related Actions
Project Plan Update or Change Request
Tailored Guidance
Reference to prescribed material
Revised Risk Mitigation Plan
Revised Issue Resolution
Escalations to Programme Office
Board Attendees
All Project Teams
Project Support Analysts
PO Facilitators
Programme Office Team
Programme Managers